## Summary
ILifa UAT Testing Gap Summary
Source: Illifa Script 4 (1).xlsx / Test tab ¦ Generated: 2026-05-31 05:26
Section | Tested - Passed | Tested - Retest/Issue | Not Tested / No Status | With Comments | Total Cases | Total test cases reviewed | 145
Unsectioned | 8 | 0 | 6 | 4 | 14 | Tested - Passed | 82
Section 2 - Authentication | 18 | 1 | 6 | 11 | 25 | Tested - Retest/Issue | 5
Section 3 - Property Owner / Agent Flows | 15 | 3 | 1 | 6 | 19 | Not Tested / No Status | 58
Section 4 - Contractor Flows | 6 | 0 | 5 | 6 | 11 | Cases with comments | 40
Section 5 - Supplier Flows | 5 | 0 | 8 | 2 | 13 | Actionable project tasks created | 37
Section 6 - User Profile & Settings | 5 | 0 | 1 | 2 | 6
Section 7 - Notifications | 1 | 0 | 2 | 1 | 3
Section 8 - Admin Panel | 24 | 1 | 12 | 8 | 37
Section 9 - Dashboard (Per-Role) | 0 | 0 | 4 | 0 | 4
Section 10 - File Uploads | 0 | 0 | 5 | 0 | 5
Section 11 - Error Handling & Edge Cases | 0 | 0 | 5 | 0 | 5
Section 12 - Performance & Cross-Browser | 0 | 0 | 3 | 0 | 3
TOTAL | 82 | 5 | 58 | 40 | 145

## Detailed Test Review
Row | Section | Subsection | Test ID | Test Step | Expected Result | Raw Status | Review Status | Tester Notes/Comments | Gap Flag
6 |  |  | 1.1.1 | Navigate to https://www.ilifapropertygroup.com | Homepage loads without errors, no broken images, no console errors | P | Tested - Passed |  | No
7 |  |  | 1.1.2 | Check the navigation bar | Logo, navigation links (Buy, Build, Services, Suppliers, Professionals) and Login/Register buttons are visible | P | Tested - Passed | Lets change colors to green | Yes
8 |  |  | 1.1.3 | Click each main navigation link | Each link navigates to the correct page without a 404 | P | Tested - Passed |  | No
9 |  |  | 1.1.4 | Resize browser to mobile width (375px) | Navigation collapses to hamburger menu; all links still accessible |  | Not Tested / No Status |  | Yes
16 |  | 1.2 Buy Property Page | R16 | Navigate to /buy- property | Property listings page loads | P | Tested - Passed |  | No
17 |  | 1.2 Buy Property Page | R17 | Browse the property listings | Property cards display image, title, price, and location | P | Tested - Passed |  | No
18 |  | 1.2 Buy Property Page | R18 | Click on a property card | Property detail page opens with full information |  | Not Tested / No Status |  | Yes
19 |  | 1.2 Buy Property Page | R19 | Verify property detail page fields | Title, price, location, description, property type, and images are displayed |  | Not Tested / No Status |  | Yes
24 |  | 1.3 Suppliers Marketplace | R24 | Navigate to / suppliers | Suppliers listing page loads | P | Tested - Passed |  | No
25 |  | 1.3 Suppliers Marketplace | R25 | Browse supplier cards | Company name, location, and category are shown |  | Not Tested / No Status | Cant see anythng | Yes
31 |  | 1.4 Professionals / Contractors | R31 | Navigate to /professionals | Contractors listing page loads | P | Tested - Passed |  | No
32 |  | 1.4 Professionals / Contractors | R32 | Browse contractor cards | Name, specialisation, and status badge are shown |  | Not Tested / No Status | No categories included .Categories included have been included in the suppliers listing | Yes
37 |  | 1.5 Build a Home Page | R37 | Navigate to /build- home | Page loads with build options/content | P | Tested - Passed |  | No
42 |  | 1.6 Services Page | R42 | Navigate to the services section | Page loads without errors |  | Not Tested / No Status | cant see it | Yes
49 | Section 2 - Authentication | 2.1 User Registration | R49 | Click "Register" in the navigation bar | Registration page loads | P | Tested - Passed |  | No
50 | Section 2 - Authentication | 2.1 User Registration | R50 | Submit the form with all fields empty | Validation errors shown for required fields | P | Tested - Passed | Does generate an error persay it just directs to the tab to complete | Yes
51 | Section 2 - Authentication | 2.1 User Registration | R51 | Enter a mismatched password and confirm password | Error: "Passwords do not match" (or similar) | P | Tested - Passed | It say invalid credentials should change to invalid email or password | Yes
52 | Section 2 - Authentication | 2.1 User Registration | R52 | Enter an invalid email format (e.g. notanemail ) | Email validation error shown | P | Tested - Passed | It say invalid credentials should change to invalid email or password | Yes
53 | Section 2 - Authentication | 2.1 User Registration | R53 | Register as Buyer with valid details ( buyer@uat-test.com) | Registration succeeds; user is redirected to dashboard or login | P | Tested - Passed |  | No
54 | Section 2 - Authentication | 2.1 User Registration | R54 | Register as Property Owner with valid details ( owner@uat- test.com ) | Registration succeeds | P | Tested - Passed | Email is correct format but does not exist ,we a verfication email code to verify users | Yes
55 | Section 2 - Authentication | 2.1 User Registration | R55 | Register as Agent with valid details ( agent@uat-test.com ) | Registration succeeds | P | Tested - Passed | Creates a property and submits does not mention that there is approval by admin before listing .Instead talks about verification which I believe we need to adjust and correct | Yes
56 | Section 2 - Authentication | 2.1 User Registration | R56 | Register as Contractor with valid details ( contractor@uat- test.com ) | Registration succeeds | P | Tested - Passed | Page not pre-populated yet 404 Error | Yes
57 | Section 2 - Authentication | 2.1 User Registration | R57 | Register as Supplier with valid details ( supplier@uat-test.com ) | Registration succeeds | P | Tested - Passed | Logical error not displayed (I put a number without enough characters) | Yes
58 | Section 2 - Authentication | 2.1 User Registration | R58 | Attempt to register with an already-registered email | Error: "Email already in use" (or similar) | P | Tested - Passed |  | No
62 | Section 2 - Authentication | 2.2 Login | R62 | Navigate to the login page | Login form loads | P | Tested - Passed |  | No
63 | Section 2 - Authentication | 2.2 Login | R63 | Submit with empty fields | Validation errors shown | P | Tested - Passed |  | No
64 | Section 2 - Authentication | 2.2 Login | R64 | Submit with wrong password | Error: "Invalid credentials" (or similar) |  | Not Tested / No Status |  | Yes
65 | Section 2 - Authentication | 2.2 Login | R65 | Submit with non-existent email | Error message shown (does not reveal if email exists) |  | Not Tested / No Status |  | Yes
66 | Section 2 - Authentication | 2.2 Login | R66 | Log in as Buyer | Redirected to buyer dashboard or homepage; name shown in navigation | P | Tested - Passed |  | No
67 | Section 2 - Authentication | 2.2 Login | R67 | Log in as Property Owner | Redirected to owner dashboard; My Properties accessible | P | Tested - Passed |  | No
68 | Section 2 - Authentication | 2.2 Login | R68 | Log in as Contractor | Redirected to contractor dashboard | P | Tested - Passed |  | No
69 | Section 2 - Authentication | 2.2 Login | R69 | Log in as Supplier | Redirected to supplier dashboard | P | Tested - Passed |  | No
70 | Section 2 - Authentication | 2.2 Login | R70 | Log in as Admin ( admin@ilifapropertygroup.com / Admin@123456 ) | Redirected to admin panel at /admin | P | Tested - Passed |  | No
74 | Section 2 - Authentication | 2.3 Logout | R74 | While logged in, click the logout button/menu item | User is logged out; redirected to homepage or login | P | Tested - Passed |  | No
75 | Section 2 - Authentication | 2.3 Logout | R75 | After logout, navigate to /dashboard or /my- properties | Redirected to login page (not shown protected content) | r | Tested - Retest/Issue |  | Yes
79 | Section 2 - Authentication | 2.4 Role-Based Access Control | R79 | Log in as Buyer, navigate to /my- properties | Access denied or redirected (Buyers cannot list properties) |  | Not Tested / No Status | need clarity not getting any errors | Yes
80 | Section 2 - Authentication | 2.4 Role-Based Access Control | R80 | Log in as Buyer, navigate to /admin | Access denied o edirected |  | Not Tested / No Status | need clarity not getting any errors | Yes
81 | Section 2 - Authentication | 2.4 Role-Based Access Control | R81 | Log in as Contractor, navigate to /admin | Access denied or redirected |  | Not Tested / No Status | need clarity not getting any errors | Yes
82 | Section 2 - Authentication | 2.4 Role-Based Access Control | R82 | Log in as Supplier, navigate to /contractors/dashboard | Access denied or redirected |  | Not Tested / No Status | need clarity not getting any errors | Yes
88 | Section 3 - Property Owner / Agent Flows | 3.1 View My Properties | R88 | Navigate to /my- properties | My Properties page loads; empty state shown if no properties yet | P | Tested - Passed |  | No
92 | Section 3 - Property Owner / Agent Flows | 3.2 Create a New Property | R92 | Click "+ Add New Property" | Property creation form loads at /my- properties/new | P | Tested - Passed |  | No
93 | Section 3 - Property Owner / Agent Flows | 3.2 Create a New Property | R93 | Submit the form without filling required fields | Validation errors shown for Title, Type, Price, City, Description | P | Tested - Passed | Doesn’t show error redirects to first column | Yes
94 | Section 3 - Property Owner / Agent Flows | 3.2 Create a New Property | R94 | Fill all required fields: Title "UAT Test House", Type "HOUSE", Price "150000", City "Harare", Description "UAT test description" | Form accepts values | P | Tested - Passed |  | No
95 | Section 3 - Property Owner / Agent Flows | 3.2 Create a New Property | R95 | Add optional fields: Bedrooms "3", Bathrooms "2", Land Size "450" | Form accepts values | P | Tested - Passed |  | No
96 | Section 3 - Property Owner / Agent Flows | 3.2 Create a New Property | R96 | Add features: "Pool, Garden, Garage" | Features accepted | P | Tested - Passed | Added this to the description not sure where to add | Yes
97 | Section 3 - Property Owner / Agent Flows | 3.2 Create a New Property | R97 | Submit the form ("List Property") | Success message shown; property appears in My Properties list with status DRAFT | P | Tested - Passed |  | No
98 | Section 3 - Property Owner / Agent Flows | 3.2 Create a New Property | R98 | Verify the property appears on the public /buy-property page (as DRAFT it may not - note th behaviour) | Note whether DRAFT properties are shown publicly | P | Tested - Passed |  | No
102 | Section 3 - Property Owner / Agent Flows | 3.3 Edit a Property | R102 | From My Properties, click "Edit" on the property just created | Edit form loads pre-filled with existing data | P | Tested - Passed |  | No
103 | Section 3 - Property Owner / Agent Flows | 3.3 Edit a Property | R103 | Change the Title to "UAT Test House - Edited" and click "Update Property" | Success message; updated title shown in My Properties list | P | Tested - Passed |  | No
104 | Section 3 - Property Owner / Agent Flows | 3.3 Edit a Property | R104 | Change the Price and save | Price updated correctly | r | Tested - Retest/Issue | refuses to update says unauthorised,changed the second time | Yes
108 | Section 3 - Property Owner / Agent Flows | 3.4 Delete a Property | R108 | From My Properties, click "Delete" on a property | Confirmation modal appears | P | Tested - Passed |  | No
109 | Section 3 - Property Owner / Agent Flows | 3.4 Delete a Property | R109 | Cancel the deletion | Modal closes; property still exists | P | Tested - Passed |  | No
110 | Section 3 - Property Owner / Agent Flows | 3.4 Delete a Property | R110 | Click "Delete" again and confirm | Property is removed from the list | P | Tested - Passed |  | No
115 | Section 3 - Property Owner / Agent Flows | 3.5 Property Verification Submission | R115 | Navigate to /verify | Verification page loads | r | Tested - Retest/Issue | Property must have at least one image before submission' | Yes
116 | Section 3 - Property Owner / Agent Flows | 3.5 Property Verification Submission | R116 | Attempt to submit property for verification | Form or instructions for document submission are shown | r | Tested - Retest/Issue | Property must have at least one image before submission' | Yes
120 | Section 3 - Property Owner / Agent Flows | 3.6 Saved Properties (as Buyer) | R120 | Log in as Buyer, browse to a property detail page | "Save" or bookmark button is visible | P | Tested - Passed |  | No
121 | Section 3 - Property Owner / Agent Flows | 3.6 Saved Properties (as Buyer) | R121 | Click "Save" | Property saved; button state changes |  | Not Tested / No Status | Need more guidance | Yes
122 | Section 3 - Property Owner / Agent Flows | 3.6 Saved Properties (as Buyer) | R122 | Navigate to /saved-properties | Saved property appears in the list | P | Tested - Passed |  | No
132 | Section 4 - Contractor Flows | 4.1 Contractor Dashboard | R132 | Navigate to /contractors/dashboard | Dashboard loads with contractor-specific stats | P | Tested - Passed |  | No
138 | Section 4 - Contractor Flows | 4.2 Contractor Profile | R138 | Navigate to /contractors/profile | Profile page loads | P | Tested - Passed |  | No
139 | Section 4 - Contractor Flows | 4.2 Contractor Profile | R139 | Navigate to create/edit profile | Profile form loads with fields: company name, specialisations, service areas, experience | P | Tested - Passed |  | No
140 | Section 4 - Contractor Flows | 4.2 Contractor Profile | R140 | Fill in profile details and save | Profile saved successfully | P | Tested - Passed |  | No
145 | Section 4 - Contractor Flows | 4.3 Service Requests | R145 | Navigate to /contractors/service-requests | List of incoming service requests is shown |  | Not Tested / No Status | Went on dashboard to services it displays 404 error | Yes
146 | Section 4 - Contractor Flows | 4.3 Service Requests | R146 | Click on a service request to view details | Full details shown with options to respond |  | Not Tested / No Status | Went on dashboard to services it displays 404 error | Yes
151 | Section 4 - Contractor Flows | 4.4 Service Request - Buyer Perspective | R151 | Log in as Buyer, navigate to /services/request | Service request form loads |  | Not Tested / No Status | Might be confusing this ,which one is this ? | Yes
152 | Section 4 - Contractor Flows | 4.4 Service Request - Buyer Perspective | R152 | Submit a service request | Success confirmation shown |  | Not Tested / No Status | Might be confusing this ,which one is this ? | Yes
153 | Section 4 - Contractor Flows | 4.4 Service Request - Buyer Perspective | R153 | Navigate to /services/my- requests | Submitted request appears in the list |  | Not Tested / No Status | Might be confusing this ,which one is this ? | Yes
158 | Section 4 - Contractor Flows | 4.5 Contractor Verification | R158 | Navigate to /verify as contractor | Verification/document upload option available | P | Tested - Passed |  | No
159 | Section 4 - Contractor Flows | 4.5 Contractor Verification | R159 | Submit verification request | Status shows as PENDING | P | Tested - Passed | Don’t know where to see this status ,though I got a notifcation that review will happen in 3 to 5 days | Yes
167 | Section 5 - Supplier Flows | 5.1 Supplier Dashboard | R167 | Navigate to /suppliers/profile | Profile form loads | P | Tested - Passed |  | No
168 | Section 5 - Supplier Flows | 5.1 Supplier Dashboard | R168 | Fill in company name, address, categories, and save | Profile saved; shown on public supplier listing |  | Not Tested / No Status |  | Yes
175 | Section 5 - Supplier Flows | 5.3 Products - Create | R175 | Navigate to /suppliers/products | Products list loads (empty if new) | P | Tested - Passed | Profile refuses to save without website | Yes
176 | Section 5 - Supplier Flows | 5.3 Products - Create | R176 | Click "Add Product" | Product creation form loads | P | Tested - Passed | says product can only be created by verified suppliers | Yes
177 | Section 5 - Supplier Flows | 5.3 Products - Create | R177 | Submit form with empty required fields | Validation errors shown | P | Tested - Passed |  | No
178 | Section 5 - Supplier Flows | 5.3 Products - Create | R178 | Fill in: Name "Cement 50kg Bag", Category, Unit Price "12.50", Stock "500", Unit "bags" | Form accepts values | P | Tested - Passed |  | No
179 | Section 5 - Supplier Flows | 5.3 Products - Create | R179 | Submit the form | Product created and appears in product list |  | Not Tested / No Status |  | Yes
184 | Section 5 - Supplier Flows | 5.4 Products - Edit | R184 | Click "Edit" on a product | Edit form loads pre-filled |  | Not Tested / No Status |  | Yes
185 | Section 5 - Supplier Flows | 5.4 Products - Edit | R185 | Update the price and save | Updated price shown in product list |  | Not Tested / No Status |  | Yes
190 | Section 5 - Supplier Flows | 5.5 Products - Delete | R190 | Click "Delete" on a product | Confirmation prompt shown |  | Not Tested / No Status |  | Yes
191 | Section 5 - Supplier Flows | 5.5 Products - Delete | R191 | Confirm deletion | Product removed from list |  | Not Tested / No Status |  | Yes
196 | Section 5 - Supplier Flows | 5.6 Supplier Marketplace - Public View | R196 | Log out, then navigate to /suppliers | Supplier is listed publicly if verified |  | Not Tested / No Status |  | Yes
197 | Section 5 - Supplier Flows | 5.6 Supplier Marketplace - Public View | R197 | Search/filter suppliers by category or city | List filters correctly |  | Not Tested / No Status |  | Yes
203 | Section 6 - User Profile & Settings | 6.1 User Profile | R203 | Navigate to /profile | Profile page loads showing current user's details | P | Tested - Passed |  | No
204 | Section 6 - User Profile & Settings | 6.1 User Profile | R204 | Update first name, last name, and phone number | Changes saved; reflected in navigation and profile | P | Tested - Passed |  | No
205 | Section 6 - User Profile & Settings | 6.1 User Profile | R205 | Upload a profile photo | Photo uploads and is displayed | P | Tested - Passed |  | No
210 | Section 6 - User Profile & Settings | 6.2 Account Settings | R210 | Navigate to /settings | Settings page loads | P | Tested - Passed |  | No
211 | Section 6 - User Profile & Settings | 6.2 Account Settings | R211 | Attempt to change password with wrong current password | Error shown |  | Not Tested / No Status | it has accepted change with wrong details | Yes
212 | Section 6 - User Profile & Settings | 6.2 Account Settings | R212 | Change password with correct current password and matching new passwords | Success message; old password no longer works | P | Tested - Passed | Successful but debutable | Yes
218 | Section 7 - Notifications |  | R218 | Trigger an action that generates a notification (e.g. property created, order placed) | Notification badge appears in header | P | Tested - Passed |  | No
219 | Section 7 - Notifications |  | R219 | Click the notification bell/icon | Notification list opens showing recent notifications |  | Not Tested / No Status | Not sure how to do this | Yes
220 | Section 7 - Notifications |  | R220 | Mark a notification as read | Notification is marked read; badge count decreases |  | Not Tested / No Status |  | Yes
231 | Section 8 - Admin Panel | 8.1 Admin Dashboard | R231 | Navigate to /admin | Admin dashboard loads with platform statistics (total users, properties, orders, revenue) | P | Tested - Passed |  | No
232 | Section 8 - Admin Panel | 8.1 Admin Dashboard | R232 | Verify stat cards: Total Users, Properties, Suppliers, Contractors | All figures shown (zeros are acceptable for a fresh install) | P | Tested - Passed |  | No
240 | Section 8 - Admin Panel | 8.2 User Management | R240 | Navigate to /admin/users | List of all registered users shown | P | Tested - Passed |  | No
241 | Section 8 - Admin Panel | 8.2 User Management | R241 | All UAT test accounts from Section 2 appear in the list | All 5 test users (Buyer, Owner, Agent, Contractor, Supplier) are listed | P | Tested - Passed |  | No
242 | Section 8 - Admin Panel | 8.2 User Management | R242 | Filter users by role (e.g. CONTRACTOR) | Only contractors shown | P | Tested - Passed |  | No
243 | Section 8 - Admin Panel | 8.2 User Management | R243 | Search for a user by name or email | Matching user shown | P | Tested - Passed |  | No
244 | Section 8 - Admin Panel | 8.2 User Management | R244 | Click on a user to view their details | User detail panel or page opens | P | Tested - Passed |  | No
245 | Section 8 - Admin Panel | 8.2 User Management | R245 | Suspend a user (e.g. the buyer test account) | User account suspended; status changes | P | Tested - Passed |  | No
246 | Section 8 - Admin Panel | 8.2 User Management | R246 | Log in as the suspended user | Login rejected with "account suspended" message | P | Tested - Passed |  | No
247 | Section 8 - Admin Panel | 8.2 User Management | R247 | In admin panel, reactivate the suspended user | User status set back to active | P | Tested - Passed |  | No
248 | Section 8 - Admin Panel | 8.2 User Management | R248 | Log in as the reactivated LIPAF | Login succeeds | P | Tested - Passed |  | No
255 | Section 8 - Admin Panel | 8.3 Property Management | R255 | Navigate to /admin/properties | All properties from all owners listed | P | Tested - Passed |  | No
256 | Section 8 - Admin Panel | 8.3 Property Management | R256 | Filter by status (DRAFT, PENDING_VERIFICATION, VERIFIED) | Properties filtered correctly | P | Tested - Passed |  | No
257 | Section 8 - Admin Panel | 8.3 Property Management | R257 | Click "Approve" on a PENDING_VERIFICATION property | Property status changes to VERIFIED |  | Not Tested / No Status |  | Yes
258 | Section 8 - Admin Panel | 8.3 Property Management | R258 | Click "Reject" and provide a reason | Property status changes; rejection reason recorded |  | Not Tested / No Status |  | Yes
259 | Section 8 - Admin Panel | 8.3 Property Management | R259 | Delete a property from admin panel | Property permanently removed |  | Not Tested / No Status |  | Yes
268 | Section 8 - Admin Panel | 8.4 Verification Management | R268 | Navigate to /admin/verifications | Pending verification requests (property, contractor, supplier) listed | P | Tested - Passed |  | No
269 | Section 8 - Admin Panel | 8.4 Verification Management | R269 | Click on a verification request | Submitted documents and details are shown |  | Not Tested / No Status |  | Yes
270 | Section 8 - Admin Panel | 8.4 Verification Management | R270 | Approve a verification request | Status changes to APPROVED; entity marked as verified |  | Not Tested / No Status |  | Yes
271 | Section 8 - Admin Panel | 8.4 Verification Management | R271 | Reject a verification with a reason | Status changes to REJECTED; reason recorded |  | Not Tested / No Status |  | Yes
278 | Section 8 - Admin Panel | 8.5 Contractor Management | R278 | Navigate to /admin/contractors | All contractor accounts listed with status badges | P | Tested - Passed |  | No
279 | Section 8 - Admin Panel | 8.5 Contractor Management | R279 | Click "Verify" on a PENDING contractor | Contractor status changes to VERIFIED |  | Not Tested / No Status | All profiles are not incomplete | Yes
280 | Section 8 - Admin Panel | 8.5 Contractor Management | R280 | Suspend a contractor | Status changes to SUSPENDED | P | Tested - Passed |  | No
281 | Section 8 - Admin Panel | 8.5 Contractor Management | R281 | Reactivate the contractor | Status changes back to VERIFIED | P | Tested - Passed |  | No
286 | Section 8 - Admin Panel | 8.6 Supplier Management | R286 | Navigate to /admin/suppliers | All supplier accounts listed | P | Tested - Passed |  | No
287 | Section 8 - Admin Panel | 8.6 Supplier Management | R287 | Click "Verify" on a PENDING supplier | Supplier status changes to VERIFIED | P | Tested - Passed |  | No
288 | Section 8 - Admin Panel | 8.6 Supplier Management | R288 | Suspend a supplier | Status changes to SUSPENDED | P | Tested - Passed |  | No
289 | Section 8 - Admin Panel | 8.6 Supplier Management | R289 | Reactivate the supplier | Status changes to active/VERIFIED | P | Tested - Passed |  | No
296 | Section 8 - Admin Panel | 8.7 Subscriptions & Payments (Admin View) | R296 | Navigate to /admin/subscriptions | Subscription list shown (may be empty) | P | Tested - Passed |  | No
297 | Section 8 - Admin Panel | 8.7 Subscriptions & Payments (Admin View) | R297 | View subscription statistics | Stats card shows plan breakdown | P | Tested - Passed |  | No
298 | Section 8 - Admin Panel | 8.7 Subscriptions & Payments (Admin View) | R298 | Navigate to payments section | Payment transaction list shown |  | Not Tested / No Status | more clarity to do this | Yes
305 | Section 8 - Admin Panel | 8.8 Analytics | R305 | Access platform analytics from admin dashboard | Analytics page/charts load | P | Tested - Passed | Need more guidance cant see anyltics | Yes
306 | Section 8 - Admin Panel | 8.8 Analytics | R306 | View user growth chart | Chart renders with available data (may be flat on a new instance) | r | Tested - Retest/Issue | No charts displayed | Yes
307 | Section 8 - Admin Panel | 8.8 Analytics | R307 | View revenue analytics | Revenue chart loads |  | Not Tested / No Status | Need more guidance cant see anyltics | Yes
308 | Section 8 - Admin Panel | 8.8 Analytics | R308 | View property market analytics | Property stats shown |  | Not Tested / No Status | Need more guidance cant see anyltics | Yes
309 | Section 8 - Admin Panel | 8.8 Analytics | R309 | View supplier performance | Supplier stats shown |  | Not Tested / No Status | Need more guidance cant see anyltics | Yes
310 | Section 8 - Admin Panel | 8.8 Analytics | R310 | View contractor performance analytics | Contractor stats shown |  | Not Tested / No Status | Need more guidance cant see anyltics | Yes
318 | Section 9 - Dashboard (Per-Role) | 9.1 General Dashboard | R318 | Log in as Owner, navigate to /dashboard | Dashboard shows: Listed Properties count, Verified Properties count, Total Views |  | Not Tested / No Status |  | Yes
319 | Section 9 - Dashboard (Per-Role) | 9.1 General Dashboard | R319 | Log in as Contractor, navigate to /dashboard | Dashboard shows: Completed Projects, Active Requests, Verified badge status |  | Not Tested / No Status |  | Yes
320 | Section 9 - Dashboard (Per-Role) | 9.1 General Dashboard | R320 | Log in as Supplier, navigate to /dashboard | Dashboard shows: Products count, Order stats |  | Not Tested / No Status |  | Yes
321 | Section 9 - Dashboard (Per-Role) | 9.1 General Dashboard | R321 | Log in as Buyer, navigate to /dashboard | Dashboard shows: Saved Properties, Viewings, Service Requests |  | Not Tested / No Status |  | Yes
326 | Section 10 - File Uploads |  | R326 | Upload a property image during property creation | Image uploads and is shown on the property |  | Not Tested / No Status |  | Yes
327 | Section 10 - File Uploads |  | R327 | Upload a profile photo in /profile | Photo uploaded and displayed |  | Not Tested / No Status |  | Yes
328 | Section 10 - File Uploads |  | R328 | Upload a product image in supplier product form | Image shown on product |  | Not Tested / No Status |  | Yes
329 | Section 10 - File Uploads |  | R329 | Attempt to upload a file larger than 10MB | Error: file too large |  | Not Tested / No Status |  | Yes
330 | Section 10 - File Uploads |  | R330 | Attempt to upload a non- image file (e.g. . exe ) | Upload rejected with an appropriate error |  | Not Tested / No Status |  | Yes
336 | Section 11 - Error Handling & Edge Cases |  | R336 | Navigate to a non-existent URL (e.g. /xyz123 ) | 404 page shown (not a blank page or crash) |  | Not Tested / No Status |  | Yes
337 | Section 11 - Error Handling & Edge Cases |  | R337 | Log out and try to access /admin directly via URL | Redirected to login (not an error page) |  | Not Tested / No Status |  | Yes
338 | Section 11 - Error Handling & Edge Cases |  | R338 | Try to access another user's property edit page by typing the URL manually | Access denied (403) or redirect |  | Not Tested / No Status |  | Yes
339 | Section 11 - Error Handling & Edge Cases |  | R339 | Submit a form with a script injection in a text field (e.g. < script>alert(1) </script> ) | Input sanitised; no alert executes |  | Not Tested / No Status |  | Yes
340 | Section 11 - Error Handling & Edge Cases |  | R340 | API health check: navigate to /api/docs | Swagger documentation page loads |  | Not Tested / No Status |  | Yes
346 | Section 12 - Performance & Cross-Browser |  | R346 | Load homepage on Chrome | Loads in under 5 seconds |  | Not Tested / No Status |  | Yes
347 | Section 12 - Performance & Cross-Browser |  | R347 | Load homepage on Firefox | Loads correctly, no broken layout |  | Not Tested / No Status |  | Yes
348 | Section 12 - Performance & Cross-Browser |  | R348 | Load homepage on Safari / Edge | Loads correctly |  | Not Tested / No Status |  | Yes

## Project Tasks
Task ID | Area | Priority | Gap / Issue | Evidence from Test Sheet | Task to Close Gap | Status | Owner/Team
T-001 | UI / Branding | Low | Navigation bar styling comment | Test 1.1.2 comment: 'Lets change colors to green' | Update the navigation bar/button/link colour scheme to approved ILifa green and verify desktop/mobile consistency. | To Do | Frontend
T-002 | Responsive UI | High | Mobile navigation not tested | Test 1.1.4 has no status | Test and fix hamburger navigation at 375px/mobile widths; ensure all main links remain accessible and no horizontal scroll. | To Do | Frontend / QA
T-003 | Buy Property | Medium | Property detail flow not completed | Tests 1.2 property card/detail fields have no status | Complete property detail page QA; fix missing image/title/price/location/description/type fields and broken routes if found. | To Do | Frontend / Backend
T-004 | Suppliers Marketplace | High | Supplier public listing appears empty | Supplier Browse Cards comment: 'Cant see anythng' | Investigate supplier listing data/rendering; ensure company name, location and category show for verified suppliers. | To Do | Frontend / Backend
T-005 | Professionals / Contractors | Medium | Contractor categories/specialisations unclear | Professionals comment: categories are missing and appear under suppliers listing | Separate supplier categories from contractor specialisations and display contractor category/status badges correctly. | To Do | Backend / Frontend
T-006 | Services | High | Services page/section not visible | Services section comment: 'cant see it' | Add/repair Services navigation and route; confirm services page loads without errors from nav and direct URL. | To Do | Frontend
T-007 | Registration Validation | High | Registration validation messages are misleading | Section 2.1 comments on empty fields, mismatched password and invalid email | Replace generic 'invalid credentials' and focus-only behaviour with clear field-level validation messages for required fields, password mismatch and invalid email. | To Do | Frontend / Backend
T-008 | Registration / Verification | High | Email verification not enforced/clear for user onboarding | Property Owner registration comment: email format accepted although mailbox does not exist; verification email/code needed | Implement/confirm email verification code flow before account activation or sensitive role access; show clear verification status and resend option. | To Do | Backend / Frontend
T-009 | Agent Registration / Property Approval | Medium | Agent registration messaging confuses verification vs admin approval | Agent registration comment: creates property/submits but does not mention admin approval before listing | Update agent/property submission workflow copy and status model to explain admin approval before public listing. | To Do | Product / Frontend
T-010 | Contractor Registration | High | Contractor onboarding/profile route returns 404 | Contractor registration comment: page not pre-populated yet, 404 error | Fix contractor post-registration redirect/profile route and pre-populate available user details where expected. | To Do | Frontend / Backend
T-011 | Supplier Registration | Medium | Supplier field validation accepts invalid numbers | Supplier registration comment: logical error not displayed for insufficient number length | Add validation rules and error messages for phone/number fields and other supplier onboarding constraints. | To Do | Frontend / Backend
T-012 | Login | Medium | Negative login cases not tested | Wrong password and non-existent email login cases have no status | Execute and fix negative login validation; ensure secure generic error for wrong password/non-existent email without revealing account existence. | To Do | QA / Backend
T-013 | Logout / Protected Routes | High | Protected route access after logout needs retest | Test 2.3 protected dashboard/my-properties status 'r' | Fix or verify logout session clearing and redirects for protected pages after logout. | To Do | Backend / Frontend
T-014 | RBAC | Critical | Role-based access denial unclear/not working | Section 2.4 Buyer/Contractor/Supplier restricted route tests have comments: 'need clarity not getting any errors' | Implement visible access-denied/redirect behaviour for restricted routes and add clear messages for Buyer, Contractor, Supplier and Admin boundaries. | Done | Backend / Frontend
T-015 | Property Creation | Medium | Required field validation UX is weak | Create Property comment: redirects/focuses to first column instead of showing validation errors | Add explicit required-field validation messages for Title, Type, Price, City and Description on property creation. | To Do | Frontend
T-016 | Property Creation | Low | Property features field unclear/missing | Create Property comment: features added to description; tester unsure where to add | Add a dedicated features input/tag field or label existing feature area clearly. | To Do | Frontend / Product
T-017 | Property Editing | High | Price update shows unauthorized intermittently | Edit Property price status 'r', comment: refused unauthorized then changed second time | Investigate edit-property authorization and save flow; remove intermittent unauthorized error and add regression test. | To Do | Backend
T-018 | Property Verification | High | Verification blocked by missing image without clear guidance | Verify tests status 'r', note: property must have at least one image before submission | Improve verification flow to show prerequisite image requirement before submission, add image upload path, and guide user to resolve it. | To Do | Frontend / Product
T-019 | Saved Properties | Medium | Save action needs guidance/verification | Saved Properties 'Click Save' has no status and note 'Need more guidance' | Clarify Save/bookmark button state, confirmation feedback, and complete QA for saved-properties list. | To Do | Frontend / QA
T-020 | Property Viewings | Medium | Property viewing flow not defined/tested | Section 3.7 has header but no test cases completed | Define, implement or document property viewing booking flow, then add UAT cases for request, confirmation and owner/buyer visibility. | To Do | Product / QA
T-021 | Contractor Service Requests | High | Contractor service request route returns 404 | Section 4.3 comments: dashboard services displays 404 | Fix /contractors/service-requests route and detail view; ensure incoming requests list and respond actions work. | To Do | Frontend / Backend
T-022 | Buyer Service Requests | Medium | Buyer service request flow unclear | Section 4.4 comments: tester confused about /services/request and /services/my-requests | Clarify buyer service request navigation/copy; complete end-to-end request submission and my-requests QA. | To Do | Product / Frontend / QA
T-023 | Contractor Verification | Medium | Verification pending status not visible to contractor | Contractor verification comment: notification shown but tester cannot see status | Expose contractor verification status in dashboard/profile and link to submitted verification details. | To Do | Frontend
T-024 | Supplier Profile | High | Supplier profile save/product gating blocks flow | Supplier products comment: profile refuses to save without website; add product says only verified suppliers | Review supplier profile required fields, mark website optional/required clearly, and ensure verification gating is explained before product creation. | To Do | Product / Frontend / Backend
T-025 | Supplier Products | High | Supplier product CRUD not completed | Product create/edit/delete tests have blanks; product creation blocked by verification | After supplier verification flow is stable, complete product create/edit/delete implementation and QA including product list updates. | To Do | Frontend / Backend / QA
T-026 | Supplier Public View | Medium | Supplier public listing filters not tested | Section 5.6 public supplier listing/search/filter tests have no status | Test and fix public supplier visibility, city/category search and filters. | To Do | Frontend / QA
T-027 | Account Security | Critical | Password change accepts wrong current password | Account settings comment: 'it has accepted change with wrong details' | Fix change-password API to validate current password before updating; add regression tests for wrong and correct current password. | Done | Backend
T-028 | Notifications | Medium | Notification actions incomplete/unclear | Notification bell/read cases have comments/no status | Document notification triggers, complete notification bell opening and mark-as-read behaviour, then retest badge count reduction. | To Do | Frontend / Backend / QA
T-029 | Admin Property Management | High | Admin approve/reject/delete property actions untested | Admin property approve/reject/delete cases have no status | Execute and complete admin property moderation flow: approve, reject with reason, and delete, with audit/status updates. | To Do | Admin / Backend / QA
T-030 | Admin Verification Management | High | Verification approve/reject details untested | Admin verification detail/approve/reject cases have no status | Complete admin verification request detail view and approve/reject workflows with reason capture and entity status update. | To Do | Admin / Backend / QA
T-031 | Admin Contractor Management | Medium | Contractor verification depends on incomplete profiles | Contractor management note: 'All profiles are not incomplete' | Validate required contractor profile completeness before admin verification; improve status badges and profile completeness messaging. | To Do | Admin / Frontend / Backend
T-032 | Admin Payments | Medium | Payments navigation unclear | Subscriptions & Payments comment: 'more clarity to do this' | Add/label payments section clearly in admin and complete transaction list QA. | To Do | Admin / Frontend
T-033 | Admin Analytics | High | Analytics charts missing or hard to find | Analytics comments: no charts displayed / need guidance | Add visible analytics navigation and render user growth, revenue, property market, supplier and contractor charts with empty-state handling. | To Do | Admin / Frontend / Backend
T-034 | Role Dashboards | High | Per-role dashboard cards not tested | Section 9 dashboard cases for Owner/Contractor/Supplier/Buyer have no status | Complete role-specific dashboard stats and QA for owner, contractor, supplier and buyer accounts. | To Do | Frontend / Backend / QA
T-035 | File Uploads | High | Upload validation not tested | Section 10 upload cases have no status | Test and enforce property/profile/product image upload, 10MB file-size limit and rejection of non-image/executable files. | To Do | Frontend / Backend / QA
T-036 | Security / Edge Cases | Critical | Error handling and security cases not tested | Section 11 cases have no status: 404, direct admin access, cross-user edit, XSS, API docs | Implement/verify 404 page, protected route redirects, cross-user 403 protection, input sanitisation/XSS prevention and API docs access policy. | Done | Backend / Frontend / QA
T-037 | Performance / Browser Compatibility | High | Cross-browser and performance not tested | Section 12 cases have no status | Run Chrome/Firefox/Safari/Edge/mobile checks and Lighthouse; fix layout/performance/accessibility issues to meet agreed thresholds. | To Do | QA / Frontend